## Summary
Sprint | Priority | Total Points | Resolved | WIP | Open | Ready to retest | Next Release
Sprint 1 |  | 58 | 50 | 0 | 8 | 0 | 0 | 0
| High | 11 | 11 | 0 | 0 | 0 | 0
| Medium | 18 | 14 | 0 | 4 | 0 | 0
| Low | 29 | 25 | 0 | 4 | 0 | 0
0
Sprint 2 |  | 54 | 31 | 1 | 19 | 3 | 0
| High | 24 | 18 | 1 | 3 | 2 | 0
| Medium | 17 | 8 | 0 | 8 | 1 | 0
| Low | 13 | 5 | 0 | 8 | 0 | 0

## Sprint 1-Log
Sl. No. | Module | Screen | Defect priority | Defect description | Logged date | Status | Resolution date | Volvo Comments | Cogent comments
1 | ALL | ALL | Low | Volvo Logo spacing not according to brand guidelines | 2019-09-13 | Resolved |  | 20-Dec: Little more corrections needed, this can be done post roll-out 06-Nov: Spacing around the logo need to corrected. As given in Sheet 1 image 1
2 | ALL | ALL | Low | Aplication name to be specifed to the right of the Volvo Logo | 2019-09-13 | Resolved | 2019-09-16 | please print "Complaint Management System" and Directly below to that Print "Volvo Trucks India" As given in Sheet 1 image 2
3 | ALL | ALL | Low | All login related fetaures and settings to be consolidated in the menu on the right | 2019-09-13 | Resolved |  | Drop down option as given in Image 3 of sheet 1
4 | ALL | ALL | Medium | Menu options on the band to be brought closer | 2019-09-13 | Resolved |  | As given in Sheet 1 Image 4
5 | ALL | ALL | Medium | The outer band povided should be removed for the MENU RIBBON | 2019-09-13 | Resolved |  | As given in Sheet 1 Image 5
6 | ALL | ALL | Low | The CMS lettering font provided near Volvo Iron Mark. | 2019-09-17 | Resolved |  | As given in Sheet 1 image 6
7 | ALL | ALL | Medium | Equi spacing to be provided and to be left aligned the parameters in the Ribbon | 2019-09-25 | Resolved
8 | Login Screen | Login Screen | Low | Mention the compatable browsers at the bottom of log in page | 2019-09-25 | Open |  | 20-Jan: The statement need to be corrected as below 23-Dec: Pls. reword the statement as "Application best compatible with Chrome & Firefox." Nov: As given in Sheet 1 Image 8
9 | Login Screen | Login Screen | High | Change the log in screen similar to the layout shown in image 9 The image will be provided later. | 2019-09-25 | Resolved |  | As given in Sheet 1 Image 9
10 | Master | All | Low | Zone to be changed to Region Zone to changed to Region in everywhere in the application | 2019-09-25 | Resolved
11 | Master | Location | Low | NOTE: Understand the link of location master with other masters. | 2019-09-25 | Resolved |  | Documented in point 38
12 | Master | Location | Low | The serial number should be given as "#" | 2019-09-25 | Resolved
13 | Master | Dealer | Low | In Dealer Master, Zone - State -City should come as cascading filters | 2019-09-25 | Resolved
14 | Master | Dealer | Low | Product option in the Dealer master should have an option of selecting both Trucks and Bus | 2019-09-25 | Resolved |  | As given in Sheet 1 Image 12
15 | Master | Dealer | Low | Seeing the possibility of specifying site in the dealer master | 2019-09-25 | Resolved
16 | Master | Product | Low | Unable to enter multiple vehicles under the same name | 2019-09-25 | Resolved
17 | Master | Product | Low | Vehicle master name to be changed to Product Master | 2019-09-25 | Resolved
18 | Master | Product | Low | The Product master shall contain Product, Segment and Model | 2019-09-25 | Resolved
19 | Master | Complaint category | Low | There must be a catergory and a sub category with edit options | 2019-09-25 | Resolved
20 | Master | User | Medium | For users who are managing multiple regions the State and the City should be auto selected . With a select option | 2019-09-25 | Resolved | 2019-12-23 | 23-Dec: Though the auto population of relevant state & cities are not happening, it is still possible to assign them by "select all". Hence, this point is marked as resolved. 16-Dec: Not resolved. Screenshot attached. Nov: While creating Regional / HO users, once the region is selected, the associated dealers and site shall automatically be assigned. There should not be a need of selecting dealers and sites for Regional / HO users.
21 | Master | Manage User | Low | What is need of User Type in Master? | 2019-09-25 | Resolved |  | Documented in point 40
22 | Master | User | Medium | The State option to be changed to Dealer Name in the Manage User | 2019-09-25 | Resolved |  | 16-Dec: The required change is done. However, the form is returing an error after submitting the details. Screenshot is attached
23 | Master | User | Low | In Manager Roles, A person whom he is Reporting To has to be added | 2019-09-25 | Resolved |  | 16-Dec: This is accomplished in User master
24 | Master | User | Low | Earmarks the users with their responsibilities | 2019-09-25 | Resolved |  | Documented in point 40
25 | Master | Customer | Low | Customer Master to be provided along with the customer designation | 2019-09-25 | Resolved
26 | Master | Product | Low | "Application" to be included along with Type & Model | 2019-10-16 | Resolved
27 | Master | User | Low | "Assign complaint to" check to be included, and only those users should have complaints assigned to them. | 2019-10-16 | Resolved
28 | Master | User | Low | Users should be responsible for "Application". This needs to be added to User Role. | 2019-10-16 | Resolved
29 | Master | Location | Low | Dealer and site to be used in Master | 2019-10-16 | Resolved
30 | Master | User | Medium | if a person leaves an organization an option for adding his manager or someone else for his role to be added | 2019-10-16 | Resolved | 2019-12-23 | 23-Dec: It is possible to assign multiple dealers / regions to a user 16-Dec: This is not working. One user is made Inactive & his reporting manager was added in his place. System returns the error "Duplicate Data". Screenshot attached
31 | Login Screen | Login | Low | 1. Overall Layout shall be in line with the content given in the URL. https://images.volvotrucks.com/login 2. Main Text "Complaint Management System" 3. Login text given below the Volvo Iron mark should be removed 4. Size of login button and Forgot Password can be retained as it is. Color of Login Button need to be aligned as per branding guidelines (CTA Blue Color) 5 . Background image will be shared shortly. 6. Spacing should be provided after "," (Refering to the compatibility text provided) 7. Compatibility text should be given at the bottom left corner of the page. | 2019-11-25 | Resolved | 2020-01-17 | 20-Jan: 7. Done 25-Dec: 4. Done 5. Retain the same image as of now. Further address the comments shared on 16th Dec 7. Pending 16-Dec: 1. Done 2. Done 3. Done 4. Pending 5. Pending with Volvo. The field & CTA portion need to be placed on a background of semi-transperant strip (screenshot attached) 6. Done. 7. The text could be pushed towards bottom of the screen, as shown in the Volvo Trucks URL in point 1. (screenshot attached) | All login page changes [MB] - Point 7 done, moved text further down, but not to bottom, so as to cover smaller screen resolution.
32 | All Screen | All | Medium | Spacing around "Iron Mark" logo to be corrected. 1. name and Iron Mark should have a space of Half the diameter of the Iron Mark around all sides. | 2019-11-25 | Resolved |  | The Volvo Iron Mark image on the top banner must have: 1. name and Iron Mark should have a space of Half the diameter of the Iron Mark around all sides.
33 | All Screen | All | Low | Arial Font to be used everywhere in the application | 2019-11-25 | Resolved
34 | Color used for buttons | All | High | Please provide the details of the color codes given in the portal for the 'submit button' the 'active inactive' status colors | 2019-11-25 | Resolved | 2019-12-20
35 | All Screen | All | Medium | The buttons from next page and previous page should be changed to "<" and ">" . | 2019-11-25 | Resolved | 2019-12-16
36 | All Screen | ALL | High | Mandatory message | 2019-11-25 | Resolved | 2019-12-23 | 23-Dec: The current option is ok at the moment Nov: Please provide a red * and display a common message as "Please Fill The Mandatory Fields"
37 | Master | Dealer | High | 1.Main dealer details have to be captured while creating the sub dealer 2. Sub dealer details need not be captured while creating main dealer. 3. Connection with Location master need to be established. 4. Dealer Code should accept 4 to 10 alpha-numerical digits. 5. Error message displayed at the time of entering the dealer details (Image 15 on screen shots) 6. Customer ID and Name should be linked when creating Site 7. Provision to add VECV Owned Dealer and Private Dealer 8. Dealer Type drop down need to changed to a) Primary Dealer b) Site Support c) Sales Office 9. Pincode filed need to be added 10. Provision to capture Type of Site - Site Support / Site Visit (This information can also be used for populating correct survey questionare) 11. Suggested to creat a seperate Master for Site and Create linkage with dealer master. 12. Assign Area Engineers as account manager for every site. | 2019-11-25 | Resolved | 2019-12-23 | 23-Dec: 3. Done 6. Done, the linkage is created in Customer employee master 10. Done 20-Dec: 3. will apply check of active locations 6. combo field for id & name 10. To do 11. Drop 16-Dec: 1. Done 2. Done 3. Pending (currently, location master contains only 8 entries, whereas, the cities mentioned in dealer master are more) 4. Done 5. Done 6. Pending 7. Done 8. Done 9. Done 10. Pending 11. Pending Comment 1: System accepts duplicate entries of Dealer code. This field should be made as unique. Comment 2: The term Site used in dealer master actually denotes "Location". Hence, this could be changed accordingly. Nov: 12 points have been listed regarding Dealer master
38 | Master | Location | High | 1. Keep only Location and State. Remove other fields | 2019-11-25 | Resolved | 2019-12-23 | 23-Dec: The ID is removed & Site name field is renamed as "Location" 20-Dec: As this master is used as a reference for Dealer ID in many other tables, suggested to fill in the ID in this master as well. 16-Dec: Pending
39 | Master | Role | High | 1. Add Reporting Role 2. Scope of Service to be mentioned | 2019-11-25 | Resolved | 2019-12-20 | 20-Dec: This is configured in User master 16-Dec: 1. Pending 2. Done
40 | Master | User | Medium | 1. User Type Should come as the 1st Field 2. Region field should come in second based on user type. Should be provided for Volvo and Dealer 3. User Role field need to given as the 3rd field. 4. The reporting to field should be auto selected when the inital 3 fields are selected. (Reason for Rearranging of Fields) 5. While creating Regional / HO users, once the region is selected, the associated dealers and site shall automatically be assigned. There should not be a need of selecting dealers and sites for Regional / HO users. 6. What is need of User Type in Master? (How is it defined and the fields for this user type defined?) 7. Evaluate the need of employee ID 8. While defining the user Primary dealer should only be available for selection. 9. When creating Area Engineer as a user the applicable sites in the given dealership need to be mapped to him. If additional Area Engineers are added to the same dealership the site list should only contain remaining sites (no single site should be assigned to multiple area engineers) | 2019-11-25 | Resolved |  | 20-Jan: The pending points can be closed, as the current UI is ok for registering the users. 20-Dec: The points 2, 3, 4, 5 & 9 are not critical from Roll-out perspective, hence, these points could be addressed post roll-out. 16-Dec: 1. Done 2. Pending 3. Pending 4. Pending 5. Pending 6. Query addressed 7. Done, incorporated 8. Done 9. Site code option is not available for Area engineer Nov: 9 points have been listed reagrding User master
41 | Master | Access | Medium | Pending elements, referring to the table given in SRS document: 1. Approval 2. Update complaint 3. Re-opening 4. Close 5. Post Complaint Survey | 25/11/2019 23-Dec-19 | Open |  | 25-Dec: ASM is unable to log a complaint
42 | Master | Role | Medium | System accepts same role multiple times (screenshot attached) | 2019-12-16 | Resolved | 2020-01-17 | 20-Jan: The role duplication is applied based on "User Type & Role". 25-Dec: Not resolved. Refer screenshot. Duplicate check is performed including the content mentioned under "User role & Responsibilities". Whereas, it should be applied only based on "Role". With this control in place, there won't be any duplicate roles reflecting while defining Escalation matrix
43 | Masters | Customer | Medium | Customer organization window: 1. The field "Site" need to be changed as "City Location" 2. Segment field in 1st row - Change this as "Customer segment". This is applicable only for Bus as of now. 3. The field "Sales Account Manager" is a title only, not a field. Hence, this field can be removed. 4. Sales POC 2 & Segment 2 need not be mandatory 5. Segment 1 & Segment 2 given in row 4 need to have dropdown list (Refer sheet Customer Master Template, range T8 to T12 for Trucks; range U8 to U10 for Bus) 6. Sales POC need to be linked with User Master (give the options similar to the one given in user master) 7. If Sales POC 2 is filled, Segment 2 should not be blank & vice versa 8. Arrange the Sales POC & Segment fields one below other 9. When the Customer contact person icon is clicked, a new window opens, however, the Customer organization data entered before is not visible. It will be good to dispay that as well in this screen. If this found difficult, look at an option of displaying certain key info viz. Organization name, Product | 2019-12-18 | Open |  | 20-Jan: 1. Open 2. Done 5. Done 6. Open. It is displaying Aftermarket people also 25-Dec: 1. Open 2. Open 4. Done 5. Open. POC 2 is not having dropdown list. 6. Open. It is displaying Aftermarket people also 23-Dec: 1. Open 2. The Customer segment dropdown need to be applicable for only Bus. And the options need to be STU, Private, Institution 3. Done 4. The fields are now made as non-mandatory. However, the Red marks need to be removed. 5. For Trucks, replace the term "Special App" with "Institutions"; POC 2 is not having dropdown list 6. Done, however, it is displaying Aftermarket people also 7. Done 8. Done 9. Done 20-Dec: The City needs to be named as "Location" | 2. - Customer segments shared earlier didn't had this list. The segments will be shared across application. Please check and suggest if these new segments are to be referred to across application. 4. Done
44 | Masters | Customer Contact | Medium | 1. Change "Locate At" to "Located at" 2. Scope of services - option to select one or more itmes from "Sales, Product, Aftermarket" 3. Mobile number duplication check need to be done across all relevant masters (including primary & secondary mobile fields) 4. "Dealer Codes Associated" should give a drop down of dealers (code, name & location - as mentioned in the template) & multiple selection should be possible. 5. Segment - give the dropdown of product segments applicable to the product type. One or more selection should be possible | 2019-12-18 | Open |  | 20-Jan: 3 & 4 are open 25-Dec: 2. Done 3. Open. To be addressed in next release 4. Open. To be addressed in next release 6. Done 23-Dec: 1. Done 2. Open 3. Due the presence of Primary & Secondary contact feature in the Customer employee data, this duplication check is not feasible at present. Suitable mechanism need to be established in Next release 4. The combo dealer details are brought in. However, use "Location", instead of "Region" 5. Done 6. New point: Complaint catagory should have multiple selection option
45 | Master | Location | Medium | Entire data in location master & complaint type master could be deleted, whereas it has dependancy in other masters & a case logged | 2019-12-20 | Resolved |  | 20-Dec: Needs to be addressed | 23-Dec-19: This is not a show stopper, can be taken up later
46 | Master | User | Low | The User name need to be split into "Title, First name, Sur name" | 2019-12-20 | Open |  |  | This is not a show stopper, can be taken up later
47 | Master | User | Medium | Reporting manager name is not getting selected (screenshot attached) | 2019-12-20 | Resolved |  | 20-Jan: Same issue remains 25-Dec: Open
48 | Master | User | Low | Users should be able to get assigned with one or more brands | 2019-12-20 | Resolved | 2019-12-23
49 | Master | Login | High | 1. Unable to login thru user IDs (averghese@VOLVO.IN & pdeyashi@volvo.in) 2. No error message is reported | 2019-12-20 | Resolved |  |  | 23-Dec-19: Please use emplooyee id and password.
50 | Master | User | High | While creating users under "Dealer / Area" type, an option to be available to assign multiple dealerships | 2019-12-20 | Resolved | 2019-12-23 | 23-Dec: The "Dealer / Area" mode of registering the user contains the option of assigning multiple dealers for the user
51 | Master | Location | High | Maharastra & Madhya Pradesh falls under both West & Central. Pls. populate these two states under both the regions. | 2019-12-23 | Resolved | 2020-01-17
52 | Master | Location | High | Unable to enter "ramagundam" as a location | 2019-12-23 | Resolved | 2019-12-24
53 | Master | Customer Contact | Medium | Secondary contact number in Customer contact master is shown as mandatory. Make this is as optional. | 2019-12-24 | Open |  | 20-Jan: Same issue remains
54 | Master | User | Medium | Even the sites need to be selected in user master. Sites should get assigned based on Main dealer association | 2019-12-24 | Resolved | 2020-01-17
55 | Master | Dealer | Medium | When creating "Site support" dealer, the drop-down list under Primary dealer also contains site support & Sales locations. It should contain only the locations marked as "Primary Dealer" in Dealer Type. | 2019-12-24 | Resolved
56 | Master | User | Low | Display the reporting manager based on name instead of ID | 2019-12-25 | Open
57 | Master | User | High | Dealer Avis Motolink is not listed in User configuration page | 2019-12-25 | Resolved
58 | User settings | User settings | Low | Need clarification on the "File settings" option given to the users (screenshot attached) | 2019-12-25 | Open

## Sprint 2-Log
Sl. No. | Module | Screen | Defect priority | Defect description | Logged date | Status | Resolution date | Volvo Comments | Cogent comments
1 | Case | Case Registeration | Low | Contact Center Module' field name to be changed to 'Mode of Complaint' | 2019-12-18 | Resolved | 2019-12-24
2 | Case | Case Registeration | High | The list of dealers should be populated based on Region selected | 2019-12-18 | Resolved |  | 25-Dec: Unable to select Region, Dealer & Location. This was resolved after correcting the master data
3 | Case | Case List | Low | Re-opening of compliant field missing | 2019-12-18 | Open |  | 25-Dec: Re-opening of cases was not required as per earlier discussions. However, we can look into this with later releases
4 | Case | Case List | High | Stage wise or update wise case progress need to be provided (Monitoring need to be provided) | 2019-12-18 | Resolved | 2019-12-24
5 | Case | Case Registeration | Low | Customer list pop up window 1. If there is no suitable result for search, display a message along side the Get data button as "No Customer found" in Red color 2. Look at the need of the pop up window (as there is no option to select a record) 3. Replace close button with an X mark in top right corner | 2019-12-18 | Open |  | 20-Jan: Not addressed 25-Dec: 1. This is implemented, however, pop-up window is also appearing. 2. Look at the possibility of giving partial search option 3. Move the X mark to top right corner
6 | Case | Case Registeration | Low | Brand selection - check if needed | 2019-12-18 | Resolved |  | 25-Dec: Addressed in point 8
7 | Case | Case Registeration | Medium | Segment - Pull the segments from customer contact person master | 2019-12-18 | Resolved
8 | Case | Case Registeration | High | Link the below fields with customer contact master 1. Product 2. Brand 3. Dealer (list the Primary Dealers pertaining to the sites assigned in customer contact master) | 2019-12-18 | Resolved
9 | Case | Case Registeration | High | Complaint get registered without selecting case owner | 2019-12-18 | Resolved |  |  | The allocation of complaint happens basis escalation matrix
10 | Case | Case Registeration | Low | The Customer details fields in case summary screen need to be re-organized (screenshot attached) | 2019-12-18 | Open |  | 20-Jan: Not addressed 25-Dec: Fields are re-organized, except "Secondary contact number". This needs to be addressed post roll-out.
11 | Case | Case Registeration | High | Time captured in case history is wrong | 2019-12-18 | Resolved | 2019-12-24
12 | Case | Case Registeration | High | Error reported after entering Observation & Comment (screenshot attached) | 2019-12-18 | Resolved | 2020-01-17 | 25-Dec: Observation field is not available for the assigned complaints
13 | Case | Case List | High | Unable to open the complaint after closing | 2019-12-18 | Resolved | 2019-12-24
14 | Case | Case Registeration | Medium | 1. Assigned to is displayed only when selecting "Re-assigned" 2. The term "description" need to be maintained as a field title (screenshot attached) | 2019-12-20 | Resolved | 2019-12-24
15 | Case | Case Registeration | High | Error reported after submitting observation & comments in case CTE19200016 | 2019-12-20 | Resolved | 2020-01-17 | 25-Dec: Observation field is not available for the assigned complaints
16 | Case | Case Registeration | High | The re-assignment is done by superadmin, however, the system captures it as done by V001040 (Partha Deyashi) Few more points are listed alongside the screenshot | 2019-12-20 | Resolved | 2019-12-24
17 | Case | Case Registeration | Low | "Comments" need to be changed to "Action comments" (Ref. screenshot) | 2019-12-20 | Resolved | 2019-12-24
18 | Case | Case Registeration | High | Status dropdown list need to be changed as below - Assigned - Acknowledged - In-progress - Waiting for Customer - Re-assigned - Completed - Closed - Dropped | 2019-12-20 | Resolved | 2019-12-24
19 | Case | Case Registeration | Medium | Observation field is updated at the time of acknowledging the complaint with customer & it doesn't change later. Hence, the content entered in this field need to be retained as is & it need not be emptied. An Edit icon can be given to allow the case owner to edit when necessery. | 2019-12-20 | Open |  | 20-Jan: Edit option is not seen 25-Dec: Observation field is missing
20 | Case | Case Registeration | Medium | 1. Aftermarket users (Venkat & Abhishek) are listed for Re-assign list of Sales complaint - [MB 16 Jan] Only the users wth assign complaint true should appear on this list relevant for the region, brand, product & segment. 2. Certain roles are not relevant for assigning complaints (Venkat & Dinakar) - refer the screenshot | 2019-12-20 | Open |  | 20-Jan: 1. Open 2. Done
21 | Case | Case Updation | Low | Fields for Root cause & Preventive action are not added | 2019-12-20 | Open
22 | Case | Case Updation | High | Fields for Post complaint survey are not added: 1. For time being, give one numeric field to capture rating & one long text field to capture customer verbatim 2. Proper questionnaire can be configured in CSS | 2019-12-20 | Resolved
23 | Case | Case Registeration | Medium | Assigned to list is populated based on org-hierarchy. There should be an option to add people from Head office as well. Hence, pls. include the list of people who are relevant for the region, brand, product & segment. [MB 16 Jan] Only the users wth assign complaint true should appear on this list, relevant for the region, brand, product & segment. | 2019-12-20 | Resolved | 2020-01-16
24 | Login | Login | Medium | Auto-logout is not happening. Configure the same at 15 minutes | 2019-12-20 | Ready to Retest
25 | Escalation | Escalation & Dealer Escalation | High | Sub complaint type & Segment need to have multiple selection option | 2019-12-23 | WIP |  | 20-Jan: Unable to create escalation, error message on "Duplicate data" is displayed (Refer Matrix ID: TS)
26 | Escalation | Escalation & Dealer Escalation | High | Unable to view the escalation line once created | 2019-12-23 | Resolved | 2019-12-24
27 | Escalation | Escalation & Dealer Escalation | High | System returns error when creating 2nd stage escalation | 2019-12-23 | Resolved | 2019-12-24
28 | Escalation | Escalation & Dealer Escalation | Medium | Window size of "CC To" need to be vertically expanded, in order to have better visibility | 2019-12-23 | Resolved
29 | Escalation | Escalation & Dealer Escalation | High | Escalation line is saved, however, not showing in the list (screenshot) | 2019-12-23 | Resolved | 2019-12-24
30 | Escalation | Escalation & Dealer Escalation | Medium | The columns in the escalation list need to be re-organized | 2019-12-23 | Open |  | 25-Dec: CC To need to be added
31 | Escalation | Escalation & Dealer Escalation | Medium | Excel download is not containing correct values, instead, it has codes | 2019-12-23 | Open
32 | Escalation | Escalation & Dealer Escalation | Medium | Edit & Delete option is not available for the lines created | 2019-12-23 | Resolved | 2019-12-24
33 | Escalation | Complaint registration intimation | High | Method of configuring the complaint registration intimation need to be clarified | 2019-12-23 | Resolved | 2019-12-24 | 25-Dec: Stage 1 & Day 1 is treated as case registration
34 | Case | Case Registeration | High | Complaint category & sub-category are not populated | 2019-12-23 | Resolved | 2019-12-24
35 | Case | Case Updation | Medium | When re-assigned, system should capture to whom it was re-assigned | 2019-12-24 | Open
36 | Case | Case Registeration | Medium | Dealer list includes Site as well. This needs to be restricted to Primary dealers | 2019-12-24 | Resolved | 2020-01-17
37 | Case | Case Registeration | High | Assignee is selected based on selection of customer's location (that is specified customer employee master) In such case, as & when a customer contact person is added, his "Location" need to be selected in "Dealer master" as well. This would be a conbursome job. Hence, it is suggested to remove the "Location" in case registration. The Assignee could be selected based on the selection of "Primary Dealer". Pls. check & revert if this will have any impact on functionality. | 2019-12-24 | Open
38 | Case | Case Registeration | High | Complaint got assigned without case description. Make this field mandatory. | 2019-12-24 | Resolved
39 | Case | Case List | Low | Reorder the fields as specified in screenshot | 2019-12-24 | Open
40 | Case | Case List | Low | Open case is not visible in case owner's page (after marking it as Waiting for Customer) | 2019-12-25 | Open |  | 20-Jan: Same issue is occuring
41 | Case | Case Updation | Medium | Display case owner name in a field, that was available in case registration window | 2019-12-25 | Resolved | 2020-01-17
42 | Case | Case Updation | Medium | The actions (such as Acknowledge, Waiting for Customer, Completed, Closed, Dropped, etc.) need to be mapped according to the user rights (Access master) | 2019-12-25 | Open
43 | Case | Case Updation | Medium | Change the Status dropdown option "Open" to "Re-open". Workflow need to be configured for this | 2019-12-25 | Open
44 | Case | Case Updation | Medium | Observations in History table: 1. Assigned - should contain to whom it was assigned 2. Acknowledged - the status should be accepted only if "Observation" field is filled-in 3. Re-Assigned - should also contain to whom it is reassigned | 2019-12-25 | Open |  | 20-Jan: 1. Open 2. Acknowledged option is not listed. Observation field is missing 3. Open
45 | Case | Case Updation | High | Completed case is not reflecting in call center window, to enable Post compaint survey | 2019-12-25 | Resolved | 2020-01-17
46 | Case | Case Updation | Low | Name of RSM (Vikash Anand) is not appearing in "Assigned to" dropdown (case 27). The RSM is already configured as the reporting manager of this case owner. | 2019-12-25 | Open |  | 20-Jan: Vikash Anand name is appearing. However, the users displayed do not have co-relation to brand, product, region, etc.
47 | Case | Case Registeration | High | Unable to assign complaint to Private Dealer, though a user (Area Service Manager) and Escalation matrix are configured | 2019-12-25 | Open |  | 20-Jan: Same issue noted for Customer Nataraj construction, Dealer Avis motolink
48 | Case | Case Updation | Medium | System allows submission of status update without any selection in "Status" dropdown | 2019-12-25 | Resolved | 2020-01-17
49 | Case | Case Updation | High | Populate the below when the user select "Completed": 1. Text field to capture the communiction given to customer 2. Drop down to capture mode of communication (Call, Meeting, E-mail, Letter) 3. Option to add attachment when mode of closure is E-mail or Letter | 2019-12-25 | Open |  | 20-Jan: Point 1 & 2 are populated even before the selection of "Completed" status Attachment should be separate for complaint logging stage & completion stage
50 | Case | Case Registeration | Low | Populate the below at the time of registering a complaint: 1. Option to add attachment 2. Attachment is mandatory when "Complaint mode" is E-mail or Letter | 2019-12-25 | Resolved | 2020-01-17
51 | Case | Case Registeration | Low | Drop down list of "Mode of complaint" 1. The options related to Help desk & Survey need to be available only for Call center user. Other options should not be available for Call center users 2. The options related to Call, Meeting, E-mail, Letter, etc. need to be available for Dealer, Regional & HO users. | 2019-12-25 | Resolved | 2020-01-17
52 | Case | Case Registeration | High | Communication mail is not trigerred upon logging the case CTW19200027. Also check the modality of configuring the communications to case received at applicable stages specified in section 3.8 of SRS document | 2019-12-25 | Ready to Retest
53 | Case | Case Registeration | High | Configure an E-mail ID for automated communications | 2019-12-25 | Ready to Retest
54 | Case | Case Registeration | Low | Registering Product complaints: 1. Vehicle model is mandatory 2. Either Chassis ID or Registration number should be entered 3. Vehicle model should have drop-down list 4. Chassis ID should accept 10 digit (Alpha numeric and special character) | 2019-12-25 | Open |  | 20-Jan: The details are asked for all category of complaints